CHANGE ORDER

Buildwell General Contracting

Change Order Number: CO-12

Project Reference: OP-215

Project Name: Riverbend Commons — Building B

Owner: Ordinal Realty Partners, LLC

Contractor: Buildwell General Contracting, Inc.

Original Contract Sum: $4,820,000.00

Date of Issue: 2026-06-18

Description of Change

This Change Order authorizes a slab revision on Level 1 of Building B to accommodate the revised structural drawings issued 2026-06-05 (SK-104 through SK-108). The revision includes deepening the slab-on-grade to 6 inches in the loading dock area, adding #5 rebar at 12" on center each way, and mobilization of the concrete subcontractor for a second pour. Site work and permit conditions are unchanged; no schedule extension is requested with this change.

Reference RFI #47 (slab depth clarification) and Submittal #22-A (concrete mix design). Contractor confirms all mobilization and material costs are captured in the line items below.

Cost Breakdown

| Item | Description | Quantity | Amount |
| --- | --- | --- | --- |
| 1 | Additional concrete — 6" slab-on-grade, loading dock area | 38 CY | $14,250.00 |
| 2 | Rebar — #5 @ 12" o.c. each way, supply + install | 1 LS | $8,600.00 |
| 3 | Concrete subcontractor mobilization — second pour | 1 LS | $3,900.00 |
| 4 | Site cleanup and demobilization | 1 LS | $1,250.00 |
|  | Subtotal |  | $28,000.00 |
|  | Contractor overhead & profit (10%) |  | $2,800.00 |
|  | TOTAL CHANGE ORDER AMOUNT |  | $30,800.00 |

Revised Contract Sum: $4,850,800.00

Approvals

Contractor: ______________________________  Date: __________

Owner:      ______________________________  Date: __________

Architect:  ______________________________  Date: __________